## Defect Categorization (hidden)
Row Labels | Count of Defect Categorization |  |  | Defect Categorization
Platform Issue | 7
Shell Issue | 2
INFA Application defects | 10
Grand Total | 19
Count of Defects Deployment Timeline | Column Labels
Row Labels | 27th Feb(During UAT Testing) | 28th Feb(Before UAT retest) | Grand Total
INFA Application defects | 2 | 8 | 10
Grand Total | 2 | 8 | 10

## Req Alignment (hidden)
| Topics | Type | Comments
1 | RE MDM SIT:When approver tries to cancel the task the screen dispalyed consists of two "cancel" buttons | Requirement | Agreed with Revert option.
2 | Are relationships editable during update process | Requirement | Count fix in place and fix should be in place with regards to the object.Fiz will be part of UAT retest(28th Feb)
3 | SITE ID,LAND and BUILDING ID are disabled while edit process | Requirement | The site id,land and building id should not be updated and will be disabled fields
4 | Data Admin-should be able to create all the 5 data objects | Requirement | Data Admin should be able to create,update,delete all the 5 objects-UAT retest(28th Feb)
5 | Demo Defect #35 | Defect | RE MDM SIT:During update for BUILDING if the gatherer is updating the process scope ,address and relationship then system is throwing error "An error has occured.For more information see the application log"
8 | Demo Defect #44 | Defect | Data Gatherer is getting error while saving the record
9 | Demo Defect #43 | Defect | RT Gatherer is able to edit and save CP data after changing Data Owner field to RT in Update view.
10 | Demo Defect #24(Issue in History) | Defect

## Legends
Cells Highlighted | Responsibility
Responsibility of Project Dev Team
Responsibility of Platform Team / ASOM Team
Responsibility of GCS Team

## Deployment Checklist
MDM - IDQ Deployment Checklist
Date of Deployment |  | 09th Sept 2020
From and To Environment |  | DEV to QA
Project Dev Resource
Emergency Contact Phone
Shell Platform Resource |  | Abhijin Patel
Line of Business |  | Group Reporting
Release Type
Deployment duration
Escalation Contact
Project Artifacts Location |  | https://sede-gf-hse.visualstudio.com/MAGMA_Platform_Service/_git/Group_Reporting
Deployment Recording
Sl# | Component | Task Details | Location | Actor | comments | Release Notes
1 | MDM | Migrate MDM Hub Config | /MDM Hub/ | Project Dev Team & Platform Team
1. Validate Source Environment ORS
2. Create Change list from QA
3. Store it in SharePoint
4. Login to Destination environment ORS
5. Validate Destination environment ORS
6. Promote all the changes from Source Environment ORS
7. Validate Destination environment ORS
2 | AVOS | Migrate Workflow configuration | /MDM ActiveVos/ | Project Dev Team & Platform Team
1. Export AVOS build as BPR file.
2. Login to AVOS with console and press deploy
3. Choose file ****.bpr and press deploy
4. Additional Validation in custom CommonPropertyFile.xml (optional)
3 | MDM Hub External Calls | Deploy External Call | /MDM External Calls/ | Project Dev Team & GCS
1. Upload created ear from Source to File storage of target server
2. Contact Shell Platform team for creation of GCS case for deployment
3. Upon receiving the mail for deployment done, please validate the deployment
4 | BDD | Deploy IDD Configuration and Queries | /MDM BDD/ | Project Dev Team & Platform Team
1. Login to Source IDD Configuration
2. Export the Application GF_Real_Estate.zip
3. Mention any additional validation is needed post import
4. Login to Destination IDD Configuration
5. Import the Application GF_Real_Estate.zip
6. Select the cmx_ors as database during import
7. Validate the Application
8. Do a full deployment of the Application
9. Login to the E360 url, Go to queries
10. Validate the queries and import the Queries.json file if not available.
5 | IDQ | Migrate IDQ Configuration | /IDQ Configurations/ | Project Dev Team & Platform Team
1. Login to Source IDQ Developer client
2. Export the XML & Zip File
3. Login to DestinationIDQ Developer client with valid id
4. Connect to Destination repository and Import the XML file
6 | IDQ SH Scripts | Migrate Unix Scripts | /IDQ Scripts/ | Project Dev Team & GCS
1. Connect to Dev IDQ server
2. Copy intended scripts and pass it to Shell Platform Team for attaching in the case.
3. Contact Shell Platform team for creation of GCS case for deployment
4. Upon receiving the mail for deployment done, please validate the deployment
7 | IDQ | Manual Verification of IDQ configuration post deployment |  | Project Dev Team
8 | MDM - IDQ | Load reference Data | /s3-mdm-shell-prod-eu-west-1/RETAIL_ORS/Distributions/Inbound/Lookup | Platform Team & Project Dev Team
1. Connect to S3 via WINSCP
2. Place cut over file in S3 bucket
3. Execute IDQ mapping to load data in MDM staging
4. Run Load process for all the Lookup Table using Batch Group in MDM hub named BG_LOAD_LOOKUPS
9 | MDM - IDQ | Load Master Data | /s3-mdm-shell-prod-eu-west-1/RETAIL_ORS/Distributions/Inbound | Platform Team & Project Dev Team
1. Connect to S3 via WINSCP
2. Place cutover Master data file in S3 bucket
3. Execute IDQ mapping to load data in MDM staging
4. Run Load process for all Master Table using Batch group in MDM hub named BG_LOAD_RE_DATA
10 | MDM - Sequence Scripts | 1. Raise a request to create the 2 oracle sequence | /MDM Scripts | Informatica Support

## Sheet9 (hidden)
add observations also as platform issues
requirement related into infa application defects
add defects which will be deployed today (on 27th ) and which on 28th

## Defect details for Pivot (hidden)
Defect ID | Summary | Priority | Status | Defect Categorization | Defects Deployment Timeline
10 | RE MDM SIT:When there is error at the child validation all the parent field validation which were passed are displayed in "red".The error goes off only by pressing tab by the user | 2 - Medium | In Process | Platform Issue
7 | RE MDM - SIT - Network tunnel timeout error | 3 - Low | In Process | Shell Issue
30 | RE MDM SIT:When approver tries to cancel the task the screen dispalyed consists of two "cancel" buttons | 2 - Medium | In Process | INFA Application defects | 28th Feb(Before UAT retest)
19 | RE MDM SIT:Building UI_Valid from date and valid to date validation issue | 3 - Low | In Process | INFA Application defects | 28th Feb(Before UAT retest)
16 | RE MDM SIT:Field name mandatory issue | 2 - Medium | In Process | INFA Application defects | 28th Feb(Before UAT retest)
11 | RE MDM SIT_NFR:When system is left idle for 10-15 mins it is asking to login again and user logins in again then the data is not populated properly in all screens | 2 - Medium | In Process | Platform Issue
31 | RE MDM SIT:System should allow only to link only one approved site record.Currently it is allowing to link more than one site record | 2 - Medium | In Process | INFA Application defects | 28th Feb(Before UAT retest)
17 | RE MDM SIT:Issues with city page for data admin | 2 - Medium | In Process | INFA Application defects | 28th Feb(Before UAT retest)
41 | Data Admin is not able to create Site Group/City | 2 - Medium | New | INFA Application defects | 27th Feb(During UAT Testing)
27 | While searching for a value in dropdown fields for all UI, search results are not aligned as in attached screenshot. | 3 - Low | New | Platform Issue
15 | RE MDM SIT:Few Fields that should be disabled for Land,Site,Building and City are in enabled state | 3 - Low | New | INFA Application defects | 28th Feb(Before UAT retest)
29 | RE MDM SIT:When user tries to "disclaim" a task the screen dispalyed have the field "disclaim" and it is better rename it to "save" to maintain uniformity | 3 - Low | New | Platform Issue
26 | RE MDM SIT:Alignment issue in the Site/Land/Building creation page | 3 - Low | New | Platform Issue
24 | Before & After Claiming, approver is not able to see Before case for Updated Fields. | 2 - Medium | New | INFA Application defects | 28th Feb(Before UAT retest)
9 | RE MDM SIT:System is slow when logged using SSO.It taken 1-2 mins to open a record | 2 - Medium | New | Shell Issue
37 | Gatherer is able to scroll, query, view data after ignoring timeout error message. | 1 - High | New | Platform Issue
34 | Data Admin not able to delete Site/Land/Building which does not have relationship | 2 - Medium | New | INFA Application defects | 27th Feb(During UAT Testing)
38 | RE MDM SIT:MDM Adminstrator is currently not working | 3 - Low | Open | Platform Issue
35 | RE MDM SIT:During update for BUILDING if the gatherer is updating the process scope ,address and relationship then system is throwing error "An error has occured.For more information see the application log" | 1 - High | Retest Failed | INFA Application defects | 28th Feb(Before UAT retest)

## INFA Application defects (hidden)
Defect ID | Summary | Priority | Status | Defect Categorization | Defects Deployment Timeline
30 | RE MDM SIT:When approver tries to cancel the task the screen dispalyed consists of two "cancel" buttons | 2 - Medium | In Process | INFA Application defects | 28th Feb(Before UAT retest)
19 | RE MDM SIT:Building UI_Valid from date and valid to date validation issue | 3 - Low | In Process | INFA Application defects | 28th Feb(Before UAT retest)
16 | RE MDM SIT:Field name mandatory issue | 2 - Medium | In Process | INFA Application defects | 28th Feb(Before UAT retest)
31 | RE MDM SIT:System should allow only to link only one approved site record.Currently it is allowing to link more than one site record | 2 - Medium | In Process | INFA Application defects | 28th Feb(Before UAT retest)
17 | RE MDM SIT:Issues with city page for data admin | 2 - Medium | In Process | INFA Application defects | 28th Feb(Before UAT retest)
41 | Data Admin is not able to create Site Group/City | 2 - Medium | New | INFA Application defects | 27th Feb(During UAT Testing)
15 | RE MDM SIT:Few Fields that should be disabled for Land,Site,Building and City are in enabled state | 3 - Low | New | INFA Application defects | 28th Feb(Before UAT retest)
24 | Before & After Claiming, approver is not able to see Before case for Updated Fields. | 2 - Medium | New | INFA Application defects | 28th Feb(Before UAT retest)
34 | Data Admin not able to delete Site/Land/Building which does not have relationship | 2 - Medium | New | INFA Application defects | 27th Feb(During UAT Testing)
35 | RE MDM SIT:During update for BUILDING if the gatherer is updating the process scope ,address and relationship then system is throwing error "An error has occured.For more information see the application log" | 1 - High | Retest Failed | INFA Application defects | 28th Feb(Before UAT retest)